Comparative Research on the Effectiveness of AI-Driven Intelligent Agent Systems and Traditional Approaches in Financial Management of IT Projects

by

Muhammadjon Tahirjanov

A report submitted in partial fulfilment of

the requirements for the degree of

MASTER OF (your Specialization)

October 2026

STUDENT DETAILS:

| Student name | Muhammadjon Tahirjanov |
| --- | --- |
| Year of study | [to be filled] |
| Current cohort | [to be filled] |
| Enrolment year | [to be filled] |

INTERNSHIP DETAILS:

| Internship provider | EPAM Systems, Inc. |
| --- | --- |
| Mentor | [to be filled] |
| Coordinator | [to be filled] |
| Internship dates | 07.09.2026 – 23.10.2026 |
| Project type | Team project: development of an AI voice agent MVP (CallMindVoice) |
| Project team members | 7 members: Muhammadjon Tahirjanov (Project Manager), 2 AI engineers, 2 backend engineers, 1 frontend engineer, 1 QA/DevOps engineer (add names) |
| Submission date | 23.10.2026 |

PROGRAM DETAILS:

| Program code and title | 60610600—Software engineering |
| --- | --- |
| Field of education | Software engineering |
| Specialization | [to be filled] |
| Program type | University major (UP) |
| Qualification level | Master’s (II) |
| Form of studies | Distance education |
| Program duration | 1.5 years |

TABLE OF CONTENTS

1. SCOPE OF INTERNSHIP	4

2. INTERNSHIP DIARY	5

3. INTERNSHIP SUMMARY	7

3.1. Project description	7

3.2. Internee role and responsibilities	8

3.3. Tools and technologies	10
…

4. CONCLUSIONS AND LESSONS LEARNED	12

4.1. General considerations	12

4.1.1. Key learnings	12

4.1.2. Challenges and their solutions	12
…

4.2. Personal implications and professional growth	13
…

5. SUBMITTED DOCUMENTS AND ARTIFACTS	15

# 1. SCOPE OF INTERNSHIP

The internship was carried out from 7 September to 23 October 2026 as a team project. Our team of seven people built CallMindVoice, an AI voice agent that answers customer-service phone calls in Uzbek, Russian and English. I worked as the Project Manager of the team.

The internship had three goals:

- deliver a working MVP of CallMindVoice by 16 October 2026;

- organise the team's work in our own Jira-like task manager: backlog, sprints, task assignment, code review and testing;

- apply my master's research topic in practice: compare the effectiveness of traditional and AI-driven approaches in the financial management of the project (cost estimation, budgeting, cost control and cost optimisation).

In scope: project planning, budgeting and cost control, team coordination, task management, risk tracking, MVP delivery, progress reporting and final documentation. Out of scope for the MVP: OCR for scanned documents, online payments and scaling to a Postgres database. These were moved to the next phase.

# 2. INTERNSHIP DIARY

| Weeks | Dates | Planned activities | Performed tasks and subtasks |
| --- | --- | --- | --- |
| Week 1 | 07.09 – 11.09 | Project initiation: requirements, stakeholders, project brief, team set-up | - Collected requirements for an Uzbek-first AI voice agent for clinics, banks and insurers - Defined the two core product rules: answers only from company documents, and handover to a human when confidence is low - Wrote the project brief and target metrics (reply latency under 800 ms, confidence threshold 0.45) - Formed the team of 7 and assigned one owner to each system layer |
| Week 2 | 14.09 – 18.09 | Planning: WBS, backlog, task manager set-up, estimates, budget | - Broke the scope into epics: knowledge search (RAG), speech, telephony, platform, console UI, billing, developer API - Set up the project board in our task manager: workflow statuses, components, task card fields - Estimated tasks with the team using Planning Poker and planned Sprint 1 - Prepared the budget estimate: developer hours, servers, AI APIs and telephony - Started the comparison of traditional (Excel, expert) and AI-assisted cost estimation for my research |
| Week 3 | 21.09 – 25.09 | Sprint 1: platform foundation and knowledge search | - Coordinated the first version of the platform: Next.js app, SQLite database, multi-tenant model, authentication and roles - Tracked the document upload and hybrid search (BM25 + vectors) tasks - Ran daily stand-ups and made sure every task had a reviewer |
| Week 4 | 28.09 – 02.10 | Sprint 1 (continued): AI and speech integration, localisation, security | - Coordinated the integration of Gemini and Uzbek speech-to-text / text-to-speech - Planned the localisation of the interface into Uzbek (Latin and Cyrillic), Russian and English - Prioritised security fixes: session cookie and server actions behind a reverse proxy - Held the Sprint 1 review and retrospective |
| Week 5 | 05.10 – 09.10 | Sprint 2: telephony, developer API, billing | - Coordinated the Asterisk phone bridge and the Twilio webhook - Tracked the REST developer API with API keys and signed webhooks - Managed the UZS billing, the new brand and the multi-agent playground tasks - Compared planned and actual sprint costs, and updated the risk list and the budget forecast |
| Week 6 | 12.10 – 16.10 | Sprint 3: voice latency, MVP release, progress video | - Led the voice latency work: streamed speech, filler phrases, barge-in and adaptive voice detection - Coordinated voice cloning, per-agent voice selection and the hands-free voice session - Released the MVP on 16 October 2026 - Recorded the progress video: project status and plan for the remaining weeks |
| Week 7 | 19.10 – 23.10 | Documentation, testing and final presentation | - Wrote the internship report and the technical documentation - Organised extra testing of real call scenarios and fixing of small bugs - Prepared the final presentation and demo - Submitted all internship documents |

# 3. INTERNSHIP SUMMARY

## 3.1. Project description

CallMindVoice (working name “Ovoz”) is a multi-tenant AI voice agent for inbound customer-service calls. It answers calls in Uzbek, Russian and English and uses only the client company's own documents, such as price lists, FAQs and policies. When the system is not sure, it hands the call to a human operator together with a summary and the full transcript.

Every call follows the same loop:

- the call arrives through Twilio or an Asterisk/FreePBX phone system;

- voice detection cuts the audio into phrases, and two speech-to-text models (Kotib for Uzbek and Whisper) run in parallel;

- the question is matched against the company's documents with keyword search (BM25) and meaning search (vectors) together;

- the system scores its confidence: above 0.45 the language model writes an answer from the found passages only, below it the call goes to an operator;

- the answer is spoken with Uzbek text-to-speech, sentence by sentence, so the caller hears the first words quickly;

- the transcript, sources, confidence and latency are saved for the operator and for analytics.

Target customers are clinics, banks, insurance companies and state service operators in Uzbekistan. The main quality target was a reply latency of under about 800 ms from the end of the caller's speech to the first audio.

## 3.2. Internee role and responsibilities

I was the Project Manager of a team of seven. I organised the team around the four layers of the system, so each layer had one clear owner:

| Role | Responsibility |
| --- | --- |
| Project Manager (me) | Scope, target metrics, phase plan, task assignment, cross-team integration, reporting |
| AI engineer — speech | Uzbek speech-to-text and text-to-speech, Whisper, voice detection |
| AI engineer — knowledge and LLM | Document chunking, embeddings, hybrid search, confidence score, Claude/Gemini/local answer engines |
| Backend engineer — platform | Database, authentication and roles, tenant isolation, REST API, webhooks, analytics |
| Backend engineer — telephony | Twilio webhook, Asterisk bridge, streaming audio, call simulator |
| Frontend engineer | Website, onboarding, operator console, live board, four-language interface |
| QA / DevOps engineer | Call-scenario testing, latency measurement, deployment, backups |

My main responsibilities were:

- Scope management: breaking the product into epics, stories, tasks and subtasks (WBS) and keeping a clear list of what is not in the MVP;

- Schedule management: planning short sprints from 7 September to the MVP release on 16 October, and tracking progress with a burndown chart and velocity;

- Finance: estimating developer hours and the cost of servers, AI APIs and telephony; the free local AI engine let us test and demo without API costs;

- Resource management: assigning tasks by layer owner and workload, and making sure every task had a reviewer from another layer.

Where and how tasks were given. All tasks were created and assigned in our own Jira-like task manager. My rule was: if a task is not in the task manager, it does not exist. Each task card had an ID, a title, a description, acceptance criteria, an assignee, a reviewer, a priority, story points, a sprint, a deadline and a component (speech, rag, platform, telephony, frontend, qa).

Every task moved through the same workflow: Backlog → To Do → In Progress → Code Review → Testing → Done. If the reviewer asked for changes or QA found a bug, the task went back to In Progress. I moved a task to Done only after checking its acceptance criteria. Git branch names contained the task ID, so every code change was linked to its task.

Our working rhythm was: backlog grooming, sprint planning with Planning Poker, a 15-minute daily stand-up (what I did, what I will do, what blocks me), a sprint review with a demo, and a retrospective.

Example task. In Sprint 3 the most important task was to cut the voice reply latency below 800 ms. The acceptance criteria were: speech is streamed sentence by sentence; fixed phrases are cached on disk; a holding phrase plays after 300 ms; the transcript is cut correctly when the caller interrupts; QA confirms the latency on test calls. The speech engineer was the assignee and the telephony engineer was the reviewer.

## 3.3. Tools and technologies

Project management tools:

- our own Jira-like task manager: backlog, Scrum board, sprints, task cards, workflow statuses;

- GitHub: repository, branches linked to task IDs, code review through pull requests;

- AI assistants for coding and documentation, guided by a project brief written for AI agents (PROJECT_BRIEF.md, CLAUDE.md).

Product technology stack:

| Layer | Technology |
| --- | --- |
| Web app and API | Next.js 16 (App Router), React 19, TypeScript |
| User interface | Tailwind CSS v4, hand-made SVG charts, four interface languages |
| Database | SQLite (node:sqlite), 16 tables |
| Knowledge search (RAG) | BM25 + vectors with Reciprocal Rank Fusion |
| Answer generation | Local extractive engine; Claude or Gemini when an API key is set |
| Speech | Uzbek STT (Kotib) + Whisper, Uzbek TTS, browser Web Speech fallback |
| Telephony | Twilio webhook, Asterisk AudioSocket bridge |
| Live updates | Server-Sent Events + in-process event bus |
| Developer API | REST /api/v1 with API keys and signed webhooks |

## 3.4. Financial management of the project

Financial management was the main focus of my work, because it is the subject of my master's research. The budget was split into four cost groups, and at the end of every sprint the planned cost was compared with the actual cost.

All figures are estimates at market rates: 7 September – 16 October (about 5.5 weeks), about 20 hours per person per week, 90,000 UZS/hour for developers, 100,000 UZS/hour for the PM, 1 USD ≈ 12,700 UZS.

| Cost group | What it includes | Planned (UZS) | Actual (UZS) | Variance (UZS) |
| --- | --- | --- | --- | --- |
| Team | PM 110→115 h, 6 developers 660→696 h | 70,400,000 | 74,140,000 | −3,740,000 (+5.3%) |
| Servers | VPS (~$60), nginx/Caddy, HTTPS, backups | 800,000 | 760,000 | +40,000 |
| AI services | Claude/Gemini test usage | 1,900,000 | 760,000 | +1,140,000 |
| Telephony | Twilio test minutes | 1,016,000 | 320,000 | +696,000 |
| Total |  | 74,116,000 | 75,980,000 | −1,864,000 (−2.5%) |

Key indicators:

- Budget variance: −2.5%. The team cost was 5.3% over plan because the voice latency work in Sprint 3 took more hours;

- Savings: AI and telephony costs were about 1.9 million UZS below plan thanks to the free local engine and the call simulator;

- CPI ≈ 0.93: about 95% of the planned scope was delivered (EV = 70.4 million UZS, AC = 76.0 million UZS);

- Effect of AI assistants: without them developers would need about 20% more time (~139 hours), so about 12.5 million UZS was saved.

Cost estimation. The story points of each task were converted into hours, and the hours into money with the hourly rate. The cost of a sprint was the sum of its tasks. Running costs (AI and telephony) were estimated as the cost of one call × the expected number of calls.

Decisions that reduced costs:

- a free local AI engine: the system works fully without API keys, so tests and demos cost almost nothing;

- automatic fallback: if Claude or Gemini fails, the system returns to the local engine;

- local 384-dimension embeddings: indexing documents needs no paid API;

- fixed phrases (greetings, holding lines) are stored as ready audio on disk and are not synthesised again for every call;

- a built-in call simulator: the team could test without paying for phone minutes.

Cost control. The system writes daily usage to the usage_daily table and invoices to the invoices table, and billing works in UZS. This is the base for real-time cost tracking. At the end of each sprint I calculated the budget variance (planned − actual) and the CPI (earned value / actual cost).

Economic effect for customers. The agent answers simple calls itself and only low-confidence calls go to an operator, so a company needs fewer operators for the same number of calls. ROI = (saved operator cost − system cost) / system cost. Example: a clinic has 3 operators earning 6 million UZS a month each. If the agent closes about 60% of calls, one operator fewer is needed, saving 6 million UZS a month. With a subscription of 2.5 million UZS a month, ROI = (6 − 2.5) / 2.5 = 1.4, or 140%: every 1 UZS spent comes back plus 1.4 UZS of profit.

## 3.5. Traditional vs AI-driven financial management

This part connects the internship with my research topic. The table compares the two approaches at each stage of financial management, with examples from CallMindVoice.

| Stage | Traditional approach | AI-driven approach | Example in CallMindVoice |
| --- | --- | --- | --- |
| Cost estimation | Expert judgement; hours × rate in Excel | Cost is predicted from the data of past sprints | Story points were converted into hours and money; AI assistants sped up estimation |
| Budgeting | The budget is made once at the start | The budget is updated every sprint from real data | Planned and actual costs were compared at the end of every sprint |
| Cost control | Monthly reports; problems are found late | Real-time tracking and early warnings about budget risk | The usage_daily and invoices tables record usage every day |
| Cost optimisation | Manual decision about which service is cheaper | An agent automatically chooses a cheaper model or the free engine | Local engine with fallback; cached audio; local embeddings |
| Labour cost | Work is split by the PM's experience | AI assistants write routine code and reduce working hours | Developers worked with AI coding assistants |
| Effectiveness (ROI) | Measured at the end of the project | Cost per call and savings are calculated all the time | The agent closes simple calls itself, reducing operator cost |

The main finding: AI-driven agents make financial management more effective. They track costs all the time, predict budget risks early and choose cheaper options automatically. However, the budget, the priorities and the final decisions stay with people. The product follows the same principle: when the AI is not confident, a human operator takes over.

## 3.6. Project status and plan for the remaining period

Status on 16 October 2026: the MVP is ready and works end to end. Finished parts: the multi-tenant platform with roles, knowledge search in three languages with a confidence score, Uzbek speech, the phone connection (Twilio and Asterisk), the operator console in four languages, UZS billing, the developer API and the voice latency improvements.

Left for after the MVP: real content for 8 of 11 industry starter packs (they still contain sample data), OCR for scanned PDFs, and streaming the model's answer directly into speech.

Plan for 17–23 October:

- 17–18 October: final report with the full financial analysis, and technical documentation;

- 19–21 October: extra testing of real call scenarios, small bug fixes, real content for more industries;

- 22–23 October: final presentation and demo, submission of all documents.

After the internship: OCR, streaming answers into speech, moving from SQLite to Postgres + pgvector and Redis, connecting Payme/Click/Stripe payments, and the first pilot with a clinic.

# 4. CONCLUSIONS AND LESSONS LEARNED

## 4.1. General considerations

The internship showed me how a project manager turns a complex AI idea into a working product in a short time. The team delivered the CallMindVoice MVP on schedule, on 16 October 2026, with seven people organised around four system layers.

### 4.1.1. Key learnings

- Clear ownership makes task assignment simple. When each layer has one owner, every new task has an obvious assignee.

- Measurable acceptance criteria remove arguments. A target like “under 800 ms” makes it clear when a task is done.

- One source of truth. Keeping every task and decision in the task manager made the progress visible to everyone.

- Cost decisions belong in the architecture. The free local engine, fallback and cached audio kept AI and telephony costs low from the first day.

- Compare plan and fact every sprint. Checking planned vs actual cost each sprint is much safer than a monthly report.

- AI is a strong helper, not a replacement. AI agents help to forecast and control costs, but the budget decisions stayed with people.

- Plan for what is not done. A written “out of scope” list protected the MVP deadline.

### 4.1.2. Challenges and their solutions

| Challenge | Solution |
| --- | --- |
| Voice replies were too slow and callers talked over the agent | Made it a Critical task with a measurable target; the team added streamed speech, cached phrases, a holding line and barge-in handling |
| External AI services cost money and were not always available | Kept a free local engine as a fallback, so tests and demos ran without API keys |
| Callers mix Uzbek (Latin and Cyrillic) and Russian | Planned one normalised search index and two speech models running in parallel |
| Tasks touching two layers (e.g. telephony + speech) were hard to assign | Split them into subtasks with one owner each and a reviewer from the other layer |
| Short timeline for the MVP | Short sprints, a strict MVP scope and a list of improvements moved to the next phase |

## 4.2. Personal implications and professional growth

As a project manager I improved my skills in budgeting, cost estimation, cost control, prioritisation and communication with developers. I learned to write tasks with clear acceptance criteria and to keep the whole team working in one shared process.

I also gained practical experience with AI-driven financial management of an IT project, which is the core of my master's research. I saw where AI tools really save time and where human judgement is still needed. This experience gives me real data and examples for my thesis and prepares me for project management roles in AI product teams.

# 5. SUBMITTED DOCUMENTS AND ARTIFACTS

The following documents and artifacts were prepared during the internship:

- Internship report (this document);

- Company supervisor's feedback form;

- Progress video with the project status and the plan for the remaining period (October 2026);

- CallMindVoice — Project Overview (technical description of the product);

- CallMindVoice — Project Manager work process document;

- Project source code: https://github.com/Kaizen-is/CallMindVoice (README, PROJECT_BRIEF, INTEGRATION and telephony bridge documentation).