0:00 — Opening

Hello. My name is Muhammadjon Tohirjonov. My thesis topic is: AI agent systems versus traditional methods in the financial management of IT projects. Today I will show my practical part. It is called FinPilot. I built it from 6 to 22 October 2026.

FinPilot is an AI finance assistant for a project manager. The idea is simple: the code counts the money, the AI explains it, and the manager decides.

FinPilot reads four kinds of data: the Jira export with worklogs, the team’s salaries, the approved budget and the invoices. It is a web app written in Python, with seven pages: Dashboard, Forecast and what-if, Business case, Ask FinPilot, Report, History and Project data.

0:30 — The problem

I tested FinPilot on a real project, CallMindVoice. It is an AI voice agent for call centres. Seven people worked on it full-time, from 22 June to 4 September 2026.

The budget was 236 million sum. The real cost was 255 million. That is 8 percent over budget, and one week late.

The team checked plan against actual every sprint, and this check always said “we are on budget”. Why? Salaries are paid every month, so the money goes out exactly as planned. But the team finished less work than planned.

1:10 — Dashboard [open Dashboard, Week 8]

This is the dashboard. I go back in time to week 8, 14 August, the end of Sprint 4.

FinPilot uses three numbers:

Plan is the money we planned to spend by today: 186 million.

Spent is the money we really spent: 185 million. That is almost the same, so the old check says everything is fine.

Earned is the planned price of the work that is really finished. It is only 174 million.

So the cost efficiency is 0.94: for one sum, we get only 0.94 sum of work. The speed is 0.93, so we are late.

FinPilot forecasts a final cost of 266 million, 12 percent over budget. This warning came three weeks before the end.

2:10 — Forecast and what-if [open Forecast & what-if]

Here are four forecast methods. For a team on salary, the best method is simple: the days we still need, times the cost of one day.

Below is “What if”. When I move a slider, for example to cut story points, the new final cost and finish date change at once. A manager can test a decision in seconds.

2:50 — Ask FinPilot [open Ask FinPilot, click “Why are we over budget?”]

Now the AI agent. I click “Why are we over budget?”

The agent uses an OpenAI model. It does not calculate by itself. It calls nine tools in my Python code, and the tools return the real numbers.

Here is the answer. The main reasons are:

a change request for noise detection and noise cleaning, 122 hours with no extra budget;

bug fixing, 129 hours;

some tasks that took much longer than estimated.

Look at this badge: number guard. It checks every number in the answer. If a number does not come from the tools, the agent must write the answer again. So the AI cannot invent numbers.

This answer took about 15 seconds and cost about one cent. The manager can accept, edit or reject it, and every step is saved in the history.

With one click, FinPilot also builds the weekly finance report as a Word file, so the manager does not have to write it by hand.

3:50 — Business case [open Business case]

Finance is also about return on investment. This page shows when CallMind earns back its cost. In the base scenario, payback takes about 20 months, so May 2028. The return on investment is 105 percent in two years. In the bad scenario, the product does not earn its cost back in two years.

4:20 — Data [open Project data → Worklogs]

The data is a Jira export: 170 tasks and about 600 worklogs, all in whole hours. I can filter by person, sprint or feature. A manager can also upload another project here.

4:40 — Results and end

I checked FinPilot’s forecasts at the end of every sprint. From Sprint 3 on, the error was only 1 to 4 percent.

So FinPilot saw the problem five weeks before the end, while the simple plan-against-actual check never showed it.

Today FinPilot works end to end, and all 16 automatic tests pass. My next step is the experiment: the same tasks done three ways, in Excel by hand, with one AI chat, and with FinPilot. I will compare the time, the wrong numbers and the causes found.

To sum up: the code counts the money, the AI explains it, and the manager decides. Thank you.